## Summary
Project Shrike
Start date : 6th of June 2013
Pessimistic man days of work : 22 days
Projected termination date : 28th of June 2013
Risk Hours Remaining: | 0
Pessimistic Hours Remaining: | 0

## Burndown
Burndown Tracking | Risk Hours Left | Pessimistic Hours Left | Date
| 153.6 | 176 | 06/06/2013
| 100.4 | 114 | 06/07/2013
| 62.8 | 70 | 06/10/2013
| 36.8 | 40 | 06/11/2013
| 0 | 0 | 06/28/2013

## Library and Control Center
Feature Work Breakdown
Shrike
Iteration 0
| Total Risk Hours: | 53.2 | Remaining: | 0
| Total Pessimistic Hours: | 62 | Remaining: | 0
Assignee | Work Item | Optimistic | Pessimistic | Risk Hours | Complete | RHL | PHL
|  |  |  | 0 | 0 | 0 | 0
Reporting Library
Jose | Move the UnikDataRouter to the Reporting Library. | 5 | 8 | 6.8 | 1 | 0 | 0
Jose | Rename the UnikDataRouter classes according to its usage. | 4 | 6 | 5.2 | 1 | 0 | 0
Jose | Move and improve the needed functionality of the TaskHub datawarehouse agent to the Reporting Library. | 5 | 8 | 6.8 | 1 | 0 | 0
Jose | Split nested classes at the WareHoseDataTask, WarehouseCatalog to improve readability. | 6 | 8 | 7.2 | 1 | 0 | 0
Jose | Refactor the WarehoseCatalog to provider interfaces for COntrolCenter and the TaskHub service. | 4 | 8 | 6.4 | 1 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
| Control Center Improvements |  |  | 0 |  | 0 | 0
| Update the ContentManager library in Control Center so that it uses the Reporting Library providers. | 8 | 12 | 10.4 | 1 | 0 | 0
| Update the ControlCenter Business components to support the changes made at the warehouseCatalog, and WarehouseTaskDescription classes | 8 | 12 | 10.4 | 1 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## TaskHub
Feature Work Breakdown
Shrike
Iteration 0
| Total Risk Hours: | 37.6 | Remaining: | 0
| Total Pessimistic Hours: | 44 | Remaining: | 0
Assignee | Work Item | Optimistic | Pessimistic | Risk Hours | Complete | RHL | PHL
[6 empty] | 0 | 0
| TaskHub Refactoring |  |  |  |  | 0 | 0
Jose | Update the TaskHub project to use the interfaces provided by the reporting library. | 6 | 8 | 7.2 | 1 | 0 | 0
Jose | Update the WorkLogic classes and separate the Test functionalily from the service functionality. | 6 | 8 | 7.2 | 1 | 0 | 0
Jose | Update and verify the UI so that it still works as expected. | 4 | 8 | 6.4 | 1 | 0 | 0
[6 empty] | 0 | 0
| TaskHub Services / Console |  |  |  |  | 0 | 0
| Create the Console and service proyects. | 7 | 12 | 10 | 1 | 0 | 0
| Test and validate behavior | 5 | 8 | 6.8 | 1 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## TAC . MEF
Feature Work Breakdown
Shrike
Iteration 0
| Total Risk Hours: | 38 | Remaining: | 0
| Total Pessimistic Hours: | 42 | Remaining: | 0
Assignee | Work Item | Optimistic | Pessimistic | Risk Hours | Complete | RHL | PHL
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
| Change from Raven to TAC |  |  | 0 | 0 | 0 | 0
| Update how the report documents are stored at the warehouse providers. (BuildinwarehouseProvider) | 6 | 8 | 7.2 | 1 | 0 | 0
| Update how the report documents are recovered at the ReportDataAnalyzer. | 6 | 8 | 7.2 | 1 | 0 | 0
| Test and verify that everything is working well | 8 | 8 | 8 | 1 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
| Providers and MEF |  |  | 0 | 0 | 0 | 0
| Modify the current BuiltInWarehouseProvider to support to implement MEF. | 6 | 9 | 7.8 | 1 | 0 | 0
| Update the WarehouseProviders and the DatawarehouseAgent class to implement the new Providers | 6 | 9 | 7.8 | 1 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0

## Improvements. Random Gen
Feature Work Breakdown
Shrike
Iteration 0
| Total Risk Hours: | 24.8 | Remaining: | 0
| Total Pessimistic Hours: | 28 | Remaining: | 0
Assignee | Work Item | Optimistic | Pessimistic | Risk Hours | Complete | RHL | PHL
|  |  |  | 0 | 0 | 0 | 0
| Reusable improvements |  |  | 0 |  | 0 | 0
| Review the ReportRoles enum at the WarehouseCatalog and make it more generic and extensible. | 6 | 8 | 7.2 | 1 | 0 | 0
| Refactor the ReportDataAnalyzer class so that it is included into a reusable component. | 6 | 8 | 7.2 | 1 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
| Random Generation |  |  | 0 |  | 0 | 0
| Move the random generation code into another component. | 4 | 6 | 5.2 | 1 | 0 | 0
| Create the needed interfaces and extend them using MEF. | 4 | 6 | 5.2 | 1 | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0